STATE OF CALIFORNIA

State Energy Resources

Conservation and Development Commission

In the Matter of					)

)	DOCKET NO.:  99-AFC-3   ERRATA TO 7-11-00

)	STATUS REPORT, INTERVENOR’S PROPOSED

## Metcalf Energy Center				)	SCHEDULING ORDER ON THE STATUS OF

)	PROCEEDINGS FOR CEC SITE LICENSING,

)	AND MOTION TO CHANGE THE ORDER

___________________________________________)	OF BUSINESS AT THE STATUS CONFERENCE

CARE provides the following errata to its Intervenor’s proposed scheduling order of 7-11-00 as follows:

The specific dates mast be determined by controlling agencies.   The total minimum remaining duration is 9 months.

CARE’s Proposed scheduling order

30 days for BACT hearings by BAAQMD, new PDOC issued

30 days from submittal of new data by the applicant to the issuance of a second PSA.

30 days of workshops and PSA comments.

30 days to FSA

15 days to issuance of BAAQMD FDOC

15 days to evidentiary hearings

30 days to rebuttal testimony submission deadline

30 days to PMPD

30 day comment period

15 days to issue Errata

15 days Commission Considers PMPD and Errata.

DATED:  July 11, 2000				respectfully submitted,

_____________________________									Michael E. Boyd

CAlifornians for Renewable Energy, Inc. (CARE)